## Gereral planning (hidden)
Training start date | April 24th | Action/discussion needed
Vendor location | Peru
Vendor headcount | 2
Working hours | 9-6pm -48 hours working week 4 days 10 hours and 1 day early 6am-10pm Brandy jumps into help with questions. Training period: 6-3
Slack channel | Soon will create
Zoom Training Room | Zoom Link: https://expedia.zoom.us/j/95059633936?pwd=K2F5WkxENEx2d3pnbzFnNG5VSlAzZz09 Meeting ID:950 5963 3936 Passcode:121212 | Luca: I have a created a "static" zoom link for all trainings to take place, it will expire at the end of May. Myself, Erika, YiQi, Brandy and Ale have been set as "hosts" (this means each one can record the session if needed and will have additional meeting controls)
Work scope | *OB subsequent batches (APM and API) *Product maintenance for centrally managed accounts | Scope might be added in the future
Tools | Expedia Partner Central-okta and SG added APM-sg-added Confluence-okta Xpresso-pc sg added-ask Dilip Outlook Kibana-decaf access-applied https://confluence.expedia.biz/display/EDECOKB/How+to+Request+Access+to+BEXBigData+-+BBD SQL and Querybook (once SQL is no longer used)-sg-Effia has to join herself. i am not the owner Excel JIRA-okta SF profile change to central operations-pending and need to wait | Confirm what the team already using Different OKTA VPN already available V- available with email
Training plan ( around 2-4 weeks for full ramp up) | Onboarding via APM (subsequent batch) Onboarding via API (subsequent batch) Disconnection Product maintenance support for centrally managed VR | integration of trianing and practice
Expectations for the role | Onboard subsequent connected VR partners and connected partner disconnections. Enable Products for centralized VR accounts, including but not limited to, creating and modifying room types, rate plans, property settings and property content Track and provide data on key performance indicators, including timelines and handle times Communicate updates with partners and internal stakeholders across various teams Collaborate with internal teams to troubleshoot problems affecting partners and ensure optimal account performance during onboarding and product enablement
Success/Performance Metrics | End to end - case age-5 days Average handle time - 100 minutes Product Maintenance AHT 40 E2E 4 Quality Score - case reviews completed by onboarding and maintenance teams to ensure case quality | Current quality check method: 3% of the case work and 97% as the target
Case volume and what to expect | 77 cases per week | based on 2022 data, may increase in 2023
SF case handling | Access to pod 7 q in SF to pick up cases.
Contact and escalation point | Expedia side: Yiqi Chen and Luca Lepori
Vendor side: Vendor side management
Meeting/catch up cadence | Monthly meet up and weekly report check | Would love to hear suggestion from Jitka based on experiences.

## Working time (hidden)
|  | Segment 1 | Segment 2 | Segment 3 |  | Segment 4
Lima |  | 6:00 - 8:00 AM | 8:00 - 10:00 AM | 10:00 - 12:00 PM | 12:00 - 1:00 PM | 1:00 - 3:00 PM | OFF
Renato and Elias |  | start Review or previous day wth Luca | New topic with Erika | New topic with Luca | Lunch | Video watch/review/case practice
London | 9:30 - 12:00 PM | 12:00 - 2:00 PM | 2:00 - 4:00 PM | 4:00 - 6:00 PM | OFF | OFF
Luca | case work, training preparation, initiatives and lunch | start Review or previous day wth Luca | case work, training preparation, initiatives and lunch | New topic with Luca | If there is call outside of working hours, please adjust the starting time
Singapore | Day time (time to start could be discussed) | 9pm - 11pm | 8:30-10:30 or 9-11pm | 7-11pm
Erika | case work, training preparation, initiatives, meeting, catch up with Luca and Yiqi |  | New topic with Erika | Total working hours should be the same. If there is meeting outside of working hours, please adjust the starting time. No Friday night training.
Brandy (Central time,same as Lima) | Training support needed in from May 1st till May 5th and May 11th till May 18th | NA | NA | NA | NA | Q&A support to vendor
Ale (London) | Training support needed in from May 1st till May 5th and May 11th till May 18th
Ale | Segment 1 | Segment 2 |  | weekly 10 hours max
Erika | Segment 3 | Tuesday and Wednesday
| Segment 1 & 2 | Monday and Thursday | no Friday
Luca | no segment 4
Brandy | Q&A segement 4 | Segment 3 | Segment 4 | any segments if not scheduled with Ale on the same day
weekly 10 hours max
List out-of-hours commitment took before the announcement
Who | When | What | YiQi Comments
Luca | 20/04 - 6PM onwards | personal commitment | noted-if there are meeting scheduled, let me know.
Luca | 01/05 - 05/05 | time off | noted-Brandy and Ale support needed
Luca | 08/05 | UK bank holiday | noted-Brandy and Ale support needed (bank holiday for Ale too)
Luca | 10/05 - 6PM onwards | Doctor appointment | outside of working hours, shoudl be ok-if there are meeting scheduled, let me know.
Luca | 16/05 - 7PM onwards | personal commitment | outside of working hours, shoudl be ok-if there are meeting scheduled, let me know.
Luca | 24/05 - 1:30PM to 2:30PM | Dentist (during lunch time) | training should be done, we need Q&A and quality check support
Luca | 29/05 | UK bank holiday | training should be done, we need Q&A and quality check support
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @YiQi Chen according to the UK employment contract, my work day ends at 5.30pm; I am happy either to start my day at 9.30am or to discuss overtime compensation for the duration of this project Reply: @Luca Lepori this is to address the UK contract law, i did not know that. please start from 9:30 and we want to ensure the total sum of working hours do not exceed the contractual hours. Reply: thank you! :)
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @YiQi Chen does this mean that during 2-4pm UK (aka 8-10am Lima) the expectation is for the vendors to be on their own whilst I either have lunch, do casework or work on initiatives? Reply: @Luca Lepori no this time the vendor will be with Erika. The vertical line represent different timezone but same time if that makes sense Reply: ah, gotcha! thank you for clarifying!
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Luca Lepori @Erika Shimada added segment guideline for easier planning
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Luca Lepori added my comments

## Week 1
Zoom Link | https://expedia.zoom.us/j/6748345021?pwd=MXB1Z2hWT3NpVkpqcXFIUC9US3d2UT09
Meeting ID | 674 834 5021
Passcode | 123456
Lima |  | 2025-07-07
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
9:00 | 10:00 | Intro to Core OTA VR | Gabriel | - Overview of this project - Review Training Plan - Verify accesses, bookmarks | https://expediacorp.sharepoint.com/:p:/r/sites/OnboardingMaintenance/_layouts/15/Doc.aspx?sourcedoc=%7B1419A756-D7C2-4861-93B1-FF4A0D7CD2AD%7D&file=Core%20OTA%20VR%20O%26M%20Presentation%20-%202025.pptx&action=edit&mobileredirect=true
10:00 | 11:00 | Intro to Confluence | Gabriel | - Overview of O&M Playbook - Searching for processes or account specs - Overview of Core OTA VR Confluence Space - Show EG Dictionary in Okta | https://expediagroup.atlassian.net/wiki/spaces/CenOps/overview?homepageId=353927170 | https://dictionary.expedia.biz/
11:00 | 12:00 | Intro to SalesForce | Elias | - What a case looks like & Pod case views - Searching (for hotels, cases, etc.) - Account pages (differences between VRPM, Connectivity Vendors, etc) - CMUI (reclassifying/creating child cases) - Reading reports (where and how) | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353937530/Salesforce+O+M
12:00 | 13:00 | Lunch | -
13:00 | 14:00 | Intro to Partner Central | Elias | - General overview of Partner Central and "Internal Tools" section - Explain concepts of "product" vs "content" - Explain concepts of "multi-unit" and "multi-rate plan" | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353935302/Partner+Central | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/354004638/VR+Concepts
14:00 | 15:00 | Free time to play with Partner Central | Self | Use the afternoon to do a recap on the day and read through confluence pages and prepare questions for next sessions
15:00 | 16:00 | Intro to APM | Elias | - Where to find APM - General overview of each hanlder - Where to find and how to read Specs | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353928812/APM+-+O+M
15:00 | 16:00 | Quiz: Salesforce | Self | https://forms.office.com/Pages/ResponsePage.aspx?id=4qLveQlUNUuXFK2gE47nbM1ZZeLB8NdKjO2bND8kCDBUMjNNQVUxSTNKMU9FWUw5M0dEWUE3SU9JRi4u | take a screenshot of your results
Lima |  | 2025-07-08
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
8:45 | 9:15 | VR Weekly TP Lima meeting | -
9:30 | 10:30 | Partner Central - Property Settings & Notification Settings | Gabriel | Explain Property Settings & Notifcation Settings in EPC. What we can see/what we can edit. | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353935467/Property+Settings+Management
10:30 | 11:30 | Deep dive: Business Models, Pricing models and RAT | Gabriel | - Explain difference between Merchant, Agency and ETP - Explain difference between PDP and OBP and LOS pricing - Explain difference between Net and Sell/LAR | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353928005/Basic+Concepts+Vocabulary
11:30 | 12:00 | Break | -
12:00 | 13:00 | APM - PS&NS | Elias | Explain PS&NS in APM and the purpose and what we update. | https://expediagroup.atlassian.net/wiki/spaces/SSG/pages/536159622/APM+Specifications
13:00 | 14:00 | Lunch | -
14:00 | 15:00 | Training cases: Property settings | Elias |  | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Property%20settings&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6&p=true&ga=1
15:00 | 16:00 | Check training cases | Elias
16:00 | 17:00 | APM Best Practices + Quiz if there's time | Self | Dos and Don'ts of APM, how to exclude columns to make a file process faster,how to interpret error messages | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353937323/Best+Practices https://forms.office.com/Pages/ResponsePage.aspx?id=4qLveQlUNUuXFK2gE47nbM1ZZeLB8NdKjO2bND8kCDBUODNXNTJaT1FKMEVRM1NMRzlZQ0M0R0swQy4u
Lima |  | 2025-07-09
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
9:00 | 9:30 | Questions from the day before? | Gabriel
9:30 | 10:00 | Break | -
10:00 | 11:00 | Partner Central - Room type & Rate Plans | Gabriel | Learn how to create/update room types & rate plans and explain what the main "building blocks" are | building blocks: shell, feeset, compensation, cancell policy
11:00 | 12:00 | APM - Room type & Rate Plans | Gabriel | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353937610/Room+Type+Management
12:00 | 12:30 | Break | -
12:30 | 13:30 | Lunch | -
13:30 | 14:30 | Partner Central: Cancellation Policies | Elias |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353927833/Creating+and+Modifying+Cancellation+Policies+in+Partner+Central
14:30 | 15:30 | Training cases: Cancellation Policies | Self |  | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Cancellation%20policies&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
15:30 | 16:30 | APM: Cancellation Policies | Elias |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353928783/Cancellation+Policy+Management
16:30 | 17:30 | Quiz: Cancellation Policies | Self | https://forms.office.com/Pages/ResponsePage.aspx?id=4qLveQlUNUuXFK2gE47nbM1ZZeLB8NdKjO2bND8kCDBUQjdSODJVUlA4Q1E1QzRZWlJFWkNTRDVJSi4u | take a screenshot of your results
Lima |  | 2025-07-10
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
9:00 | 9:30 | Training Cases Review from yesterday | Gabriel
9:30 | 10:30 | Partner Central: Deposit | Gabriel |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353927172/Deposit+Policy+Management
10:30 | 11:00 | Break | -
11:00 | 12:00 | APM: Deposits | Elias |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353927172/Deposit+Policy+Management
12:00 | 13:00 | Lunch | -
13:00 | 14:00 | Training Cases: Deposit (EPC) | Self | Elias to give Juan all the training cases | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Deposits&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
14:00 | 15:00 | Training Cases: Cancellation Policies (APM) | Self |  | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Cancellation%20policies&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
15:00 | 16:00 | Training Case: Deposit (APM) | Self |  | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Deposits&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
Lima |  | 2025-07-11
Start Time | End Time | Session Name | Who |  | Notes/feedback/questions/resources
9:00 | 9:30 | Training Cases Review from yesterday | Gabriel
9:30 | 10:30 | Partner Central: Compensation | Gabriel |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929742/Updating+Compensation+Rules+in+Partner+Central
9:30 | 11:00 | Break | -
11:00 | 12:00 | APM: Compensation | Gabriel |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929607/Compensation+Rule+Management
12:00 | 13:00 | Training cases: Compensation | Self |  | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Compensation%20Rules&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
13:00 | 14:00 | Lunch | -
14:00 | 15:30 | Partner Central + APM: Taxes | Elias | - Explain how to load/update taxes both in PC and APM - Introduce the PQC Team and Tax Inclusive lists - Show the Master Tax Report | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353940988/How+to+Load+Taxes
15:30 | 16:30 | Quiz: Deposits and Compensation | Self | https://forms.office.com/Pages/ResponsePage.aspx?id=4qLveQlUNUuXFK2gE47nbM1ZZeLB8NdKjO2bND8kCDBUREFLN0VIRUdRUkM1MU5UMTBHMExDUjJQSi4u | take a screenshot of your results
16:30 | 17:30 | Free time to explore Partner Central/play with taxes and fees + self review | Self

## Week 2
Zoom Link | https://expedia.zoom.us/j/6748345021?pwd=MXB1Z2hWT3NpVkpqcXFIUC9US3d2UT09
Meeting ID | 674 834 5021
Passcode | 123456
Lima |  | 2025-07-14
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
8:30 | 9:00 | Questions for Week 1 learning + any revision required? | Gabriel | Review Week 1's learning and advise if there are any items we need to re-learn/clarify?
9:00 | 10:00 | Partner Central: Fee Sets | Gabriel |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929609/FeeSet+and+Service+Charge+Management
10:00 | 11:00 | APM: FeeSets | Gabriel |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929609/FeeSet+and+Service+Charge+Management
11:00 | 13:00 | Training Cases: Fee Set (EPC + APM) | Self | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Fee%20sets&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
13:00 | 14:00 | Lunch | -
14:00 | 15:00 | Partner Central: Rate Plan Linkages | Elias |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929605/Rate+Plan+Linkage+Management
15:00 | 16:00 | APM: Rate Plan Linkages | Elias |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929605/Rate+Plan+Linkage+Management
16:00 | 17:00 | Training cases: Rate Plan Linkages | Self | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Rate%20Plan%20Linkage&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
Lima |  | 2025-07-15
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
8:45 | 9:15 | VR Weekly TP Lima meeting | -
9:30 | 10:15 | Partner Central: Distribution Rules | Gabriel |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353928030/Distribution+Rules+Page
10:15 | 11:15 | Partner Central: Regional Rules & Compliance | Gabriel | TPIDs, ROCS tool | https://expediagroup.atlassian.net/wiki/spaces/RegOps/pages/460360215/EG+Regulatory+Requirements?search_id=926a5f34-4218-485f-a3c2-579e87ecb58b&additional_analytics=queryHash---748d8735530048af931c59b9a6566dfc6d39276fa049c6050f1e75d324aad8da
11:15 | 12:00 | Break - free time to review | Self
12:00 | 13:00 | Lunch | -
13:00 | 14:00 | APM: Regulatory Import | Gabriel | Explain process of exporting the settings first to update the regulatory information (batch) | https://expediagroup.atlassian.net/wiki/spaces/SSG/pages/536450706/Regulatory+Information+Import
14:00 | 15:00 | Difference between VRBO and Core OTA | Elias
15:00 | 16:00 | Partner Central: Promotions | Elias |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929552/DRR+Management
16:00 | 17:00 | APM: Promotions | Elias
17:00 | 17:45 | Training cases: Promotions | Self |  | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Promotions&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
Lima |  | 2025-07-16
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
9:00 | 10:00 | Questions from the day before? / Review Afternoon Training cases & Connectivity Overview: EQC, EC/EC2 & Core OTA API capabilities crash course | Gabriel | - Learn about the main APIs/types of connectivity O&M works with & how they differ from each other (AR, ARI, BRBC, BN, Syncbook) - Learn how to identify the connectivity type & vendor for a given property. - Understand how connectivity affects the way O&M creates room types & rate plans - Understand how vendors push rates & availability to Expedia depending on the connectivity type | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353927227/Connectivity
10:00 | 11:00 | Video: Connectivity at EG | Self | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/_layouts/15/stream.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Recordings%2FO%26M%20Connectivity%20Training%2Emp4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview%2Ecdb8efcb%2Db8dc%2D4909%2D8965%2D66c942ad81df
11:00 | 12:00 | Training cases: Connectivity basics | Elias |  | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Connectivity%20basics&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
12:00 | 13:00 | Lunch | -
13:00 | 14:00 | APM: EQC Export + Import | Elias | Brief explanation of what EQC export and import does and why we need them
14:00 | 15:00 | Connectivity File | Elias | Break - free time to review | No practice cases required for EQC export + import
15:00 | 15:30 | Break - free time to review | Self
15:30 | 16:30 | Quiz: Connectivity | Self | https://forms.office.com/Pages/ResponsePage.aspx?id=4qLveQlUNUuXFK2gE47nbM1ZZeLB8NdKjO2bND8kCDBUREc5VFc2U09UWlNHUUZURzRGQ0ZGUVoyOS4u | take a screenshot of your results
Lima |  | 2025-07-17
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
9:00 | 9:30 | Questions from the day before? / Review Afternoon Training cases | Gabriel | recap day before / check training case from yesterday afternoon
9:30 | 11:00 | break
11:00 | 11:30 | Introduction to VR API OB in Core OTA | Elias | How API certified connectivity vendors + VR PMs onboard on Expedia? Explain MinGoLive report | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353937319/VR+API+Onboarding+Process+-+High+Level+Overview
11:30 | 12:30 | Lunch | -
12:30 | 13:30 | Xpresso Rebuilds | Elias |  | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929586/Xpresso+rebuild+process
13:30 | 14:30 | Practice Cases | Self
14:30 | 17:30 | Case work shadowing | Elias
Lima |  | 2025-07-18
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
9:00 | 9:30 | Questions from the day before about VR API or API onboarding | Gabriel
9:30 | 10:30 | Partner Central & APM: Content + Attributes | Gabriel | - Explain the difference between property level and room level content - Explain how each selection triggers an attribute and where to see attributes in PC - Explain what SCIIs are and show the SCII Conf page from Central Content Team
10:00 | 11:00 | Training cases: Content updates |  |  | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Cases%2FO%26M%20training%20cases%20%2D%20Content%20updates&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6
11:00 | 12:00 | Lunch
12:00 | 13:00 | Training cases: Content updates | Self | Send a slack message to Elias to advise once done
13:00 | 14:00 | Troubleshooting & Investigation P1 - P4 | Self | Recording Links - video to watch starts with 'O&M Troubleshooting & Investigation Training..': https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/Shared%20Documents/Forms/AllItems.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Recordings&viewid=021abbc8%2D843c%2D4feb%2D9eb5%2D68a7ac17bff6 Basics - How to approach troubleshooting/investigation cases – what settings/tools to check, dos and don’ts - When and how we should contact TST - How to communicate with the partner | Each video is about 45 - 55 mins long
14:00 | 15:00
15:00 | 15:30
15:30 | 16:30 | Review documentation | Self | Review all the topics you've learnt this week by going through the recordings/documenation links on Confluence :) Next week, you'll be doing more APM work for RT & RP, plus hopefully some real cases!

## Week 3
Zoom Link | https://expedia.zoom.us/j/6748345021?pwd=MXB1Z2hWT3NpVkpqcXFIUC9US3d2UT09
Meeting ID | 674 834 5021
Passcode | 123456
Lima |  | 2025-07-21
Start Time | End Time | Session Name | Who |  | Notes/feedback/questions/resources
8:00 | 8:30 | Catch up on email/slack + listen to any recordings left from Friday | Self
8:30 | 9:00 | Questions for Week 2 learning + any revision required? | Renato
9:00 | 10:00 | Dataloader | Renato
10:00 | 11:00 | Break
11:00 | 12:00 | Intro to QueryBook | Self - recording | https://expediacorp.sharepoint.com/sites/OnboardingMaintenance/_layouts/15/stream.aspx?id=%2Fsites%2FOnboardingMaintenance%2FShared%20Documents%2FO%26M%20Training%20Material%2FO%26M%20Training%20Recordings%2FO%26M%20Querybook%20Training%2Emp4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview%2E56395339%2D6276%2D49b5%2D9787%2D2598ab292eb9
12:00 | 13:00 | Lunch
13:00 | 14:00 | Q&A with Renato | Renato
14:00 | 15:00 | Shadow Elias | Elias
15:00 | 16:00 | Casework | Self | Try to do the practice cases listed in your SF queue
16:00 | 16:30 | Review the day | Self
Lima |  | 2025-07-22
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
7:30 | 8:30 | Catch up on email/slack + Confluence Reading on any topics + listen to any recordings left | Self
8:45 | 9:15 | VR Weekly TP Lima meeting | -
9:30 | 10:30 | Master ID File | Renato | how to access to master ID folder + functionalities
10:30 | 12:30 | VR Onboarding (APM) | Gabriel
12:30 | 13:30 | Lunch
13:30 | 14:30 | Case Shadowing | Elias
14:30 | 15:30 | Casework | Self | Try to do the practice cases listed in your SF queue
15:30 | - | Casework | Self | Try to do the practice cases listed in your SF queue
Lima |  | 2025-07-23
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
9:00 | 9:20 | Q&A + Refresh on SalesForce use + checking accesses | Renato
9:20 | 10:00 | Partner Central User Management (PC & APM) | Gabriel | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353929550/EPC+User+Management
10:00 | 10:30 | Break | -
10:30 | 23:30 | Shadowing a disconnection | Renato
23:30 | 12:30 | Practice Cases | Self
12:30 | 13:30 | Disconnections | Renato
13:31 | 14:00 | Lunch | -
14:00 | 15:00 | Strategic VR Accounts | Renato | Documentation to read
15:00 | 15:30 | Case Shadowing TP Agent | Any agent Lima team
15:30 | 16:30 | Practice Cases | Self
16:30 | 17:00 | Practice Cases | Self
Lima |  | 2025-07-24
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
7:30 | 9:00 | Catch up on email/slack + Confluence Reading on any topics + listen to any recordings left | Self
9:00 | 10:00 | EC+ | Renato
10:00 | 11:00 | Real Casework | Self
11:00 | 12:00
12:00 | 13:00 | Lunch | -
13:00 | 15:00 | BMC | Elias
15:00 | 16:00 | Fellow teams / Escalations | Renato | https://expediagroup.atlassian.net/wiki/spaces/CenOps/pages/353935028/Fellow+Teams
16:00 | 17:00 | Real Casework | Self
Lima |  | 2025-07-25
Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions/resources
9:00 | 10:00 | Review of the Week 3 + Q/A | Renato
10:00 | 11:00 | POD7 details | Renato
11:00 | 12:00 | Case Shadowing TP Agent | Any agent Lima team
12:00 | 13:00 | Lunch
13:00 | 14:00 | Real Casework | Self
14:00 | 15:00 | Real Casework | Self
15:00 | 15:30 | Real Casework | Self
15:30 | 16:30

## Topics to cover (hidden)
Here I just want to add the full list of topics we want to cover with the Vendors and in which order they should be presented. We can then lay them out in the schedule. Each session should be intended as 1h
Order |  | Topic |  | Comments | With Trainer or Alone?
39 | 1 | Partner Central - Room type and rate plans | PC |  | Trainer
11 | 1 | Training cases: Deactivation/reactivations, occupancy updates, room name updates (PC) | PC Training |  | Alone
16 | 1 | APM export | APM | Video from Josh | xRemoved
25 | 1 | Training cases: Deactivation/reactivations, occupancy updates, room name updates (APM) | APM Training |  | Alone
10 | 1 | Demo: Room type or rate plan deactivation/reactivations, occupancy updates, room name updates |  |  | Trainer
40 | 1.5 | Training cases: Room Type & Rate Plan Creation (PC) | PC Training |  | Alone
24 | 1.5 | APM RTRP import | APM |  | Trainer
47 | 1.5 | Training cases: Room Type & Rate Plan Creation (APM) | APM Training |  | Alone
59 | 2 | Partner Central - Property Settings | PC | move up to the schedule | Trainer
60 | 2 | APM - PS&NS | APM |  | Trainer
61 | 2 | Training cases: Property settings | PC+APM Training |  | Alone
28 | 3 | Partner Central - Cancellation policies | PC |  | Trainer
29 | 3 | Training cases: Cancellation policies (PC) | PC Training |  | Alone
30 | 3 | APM - Cancellation policies | APM |  | Trainer
31 | 3 | Training cases: Cancellation policies (APM) | APM Training |  | Alone
32 | 3 | Quiz: Cancellation policies | Quiz |  | Alone
35 | 4 | Partner Central - Deposits | PC |  | Trainer
36 | 4 | Training cases: Deposits (PC) | PC Training |  | Alone
44 | 4 | APM - Deposits | APM | Seperated Compensation | Trainer
45 | 4 | Training cases: Deposits (APM) & Compensation Rules (APM) | APM Training | Seperated Compensation | Alone
46 | 4 | Quiz: Deposits & Compensation Rules | Quiz |  | Alone
33 | 5 | Partner Central - Compensation Rules | PC |  | Trainer
34 | 5 | Training cases: Compensation Rules (PC) | PC Training |  | Alone
44.5 | 5 | APM - Compensation Rules | APM |  | Trainer
37 | 6 | Partner Central - FeeSets | PC |  | Trainer
38 | 6 | Training cases: Fee sets (PC) | PC Training |  | Alone
42 | 6 | APM - Feeset | APM |  | Trainer
43 | 6 | Training cases: Fee sets (APM) | APM Training |  | Alone
48 | 7 | Partner Central - Rate Plan Linkage | PC |  | Trainer
49 | 7 | APM - Rate Plan Linkage | APM |  | Trainer
105 | 7 | Quiz: Taxes and fees | Quiz |  | Alone
50 | 7 | Training cases: Rate Plan Linkage | PC+APM Training |  | Alone
76 | 7 | Connectivity file / tax exercise | Training |  | Alone
73 | 7 | Partner Central + APM - Taxes |  |  | Trainer
51 | 8 | Partner Central - Promotions | PC |  | Trainer
53 | 8 | Training cases: Promotions (PC) | PC Training |  | Alone
52 | 8 | APM - DRR | APM |  | Trainer
53.5 | 8 | Training cases: Promotions (APM) | APM Training |  | Alone
63 | 9 | Partner Central - Content | PC | general knowledge, content dos and don't | Trainer
65 | 9 | Training cases: Content updates | PC Training |  | Alone
64 | 9 | APM - Attributes | APM |  | Trainer
92 | 10 | Partner Central - Regulatory & Compliance | PC | potential week 4-compliance rules | Trainer
92.5 | 10 | APM - Regulatory & Compliance | APM |  | Trainer
23 | 11 | Partner Central + APM - EPC Users | PC | Later | Trainer
86 | 12 | Partner Central - Distribution Rules | PC |  | Trainer
27 |  | Quiz: APM Best Practices | Quiz |  | Alone
89 |  | Quiz: Connectivity | Quiz |  | Alone
9 |  | Quiz: Salesforce | Quiz |  | Alone
93 |  | Exercise - Regional Rules | PC+APM Training |  | Alone
17 |  | APM Specs |  |  | Trainer
91 |  | Central VR account overview and resources |  | potential week 4 | Trainer
122 |  | Central VR do and don'ts and account specifics |  | one session per account by Brandy | Trainer
62 |  | Deeper dive on business models, pricing models, and RAT |  |  | Trainer
101 |  | Demo: Onboarding |  |  | Trainer
79 |  | Disconnection Process |  |  | Trainer
19 |  | Free time to play with APM exports/browse APM specs once done with training cases |  |  | Alone
55 |  | Intro to API |  | Andressa's recording | Trainer
74 |  | Intro to Connectivity file |  |  | Trainer
83 |  | Intro to Kibana |  | There's a recording for this by Josh | Alone
4 |  | Intro to Partner Central |  |  | Trainer
7 |  | Intro to Salesforce |  |  | Trainer
84 |  | Kibana exercise |  |  | Alone
98 |  | Master ID file |  | There's a recording for this | Alone
1 |  | O&M Overview and Review of Training Plan |  |  | Trainer
97 |  | Onboarding process APM and API |  |  | Trainer
5 |  | Overview of O&M Playbook (Confluence) & LSP Central |  |  | Trainer
85 |  | Training cases - Kibana |  |  | Alone
18 |  | Training cases: APM export |  |  | Alone
57 |  | Training cases: Connectivity basics |  |  | Alone
3 |  | Verify Access, Bookmarks, Slack channels |  |  | Trainer
54 |  | Workday training: Connectivity at Expedia Group |  | Need to download video from workday | Trainer
2 |  | A day in the life of a Specialist |  |  | xRemoved
56.5 |  | APIs & Connectivity Overview |  | not needed | xRemoved
12 |  | Aspect |  |  | xRemoved
114 |  | Attribute-based shopping |  |  | xRemoved
15 |  | Basecamp |  |  | xRemoved
26 |  | Best practices for partner communication |  |  | xRemoved
108 |  | Case Reviews |  |  | xRemoved
8 |  | Casework in Salesforce |  | Duplicate | xRemoved
6 |  | Confluence & Partner Central exploration |  |  | xRemoved
104 |  | Connectivity conversions |  |  | xRemoved
56 |  | Connectivity Overview: EQC, EC/EC2 |  | not needed | xRemoved
121 |  | Demo: Investigation & Troubleshooting |  | Not needed - is primarily part of maintenance/post onboarding | xRemoved
95 |  | Demo: x-out tool |  |  | xRemoved
115 |  | Display Logic |  |  | xRemoved
96 |  | Exercise - x-out tool |  |  | xRemoved
82 |  | Exercise: Misrouting cases |  |  | xRemoved
78 |  | Functional audit |  |  | xRemoved
67 |  | Functional audits |  |  | xRemoved
99 |  | How to build a property shell (APM) |  | Duplicate of APM - PS&NS | xRemoved
112 |  | Intro to AMEX |  |  | xRemoved
71 |  | Intro to Business model conversions |  |  | xRemoved
20 |  | Intro to Excel (useful formulas for O&M) |  | Pending asking vendor | xRemoved
90 |  | Intro to Integration |  |  | xRemoved
80 |  | Intro to LSP |  |  | xRemoved
94 |  | Intro to macros - Sabre Automated Tool |  |  | xRemoved
75 |  | Intro to other EG teams |  |  | xRemoved
87 |  | Intro to SQL |  | There's a recording for this | xRemoved
14 |  | Intro to Tableau & how O&M measures performance |  |  | xRemoved
81 |  | Intro to TRM |  |  | xRemoved
111 |  | Intro to VR |  |  | xRemoved
117 |  | Investigation & Troubleshooting |  | Not needed - is primarily part of maintenance/post onboarding | xRemoved
66 |  | O&M quality |  |  | xRemoved
68 |  | O&M's scope: what we do and don't process |  |  | xRemoved
106 |  | Partner Central: Change History |  | Not needed - is primarily part of maintenance/post onboarding-evaluate later | xRemoved
119 |  | Partner Central: Reservation lookup |  | Not needed - is primarily part of maintenance/post onboarding | xRemoved
58 |  | Playbook review / Casework |  |  | xRemoved
13 |  | Pod amin tasks |  |  | xRemoved
41 |  | Queue Management & Prioritization |  |  | xRemoved
118 |  | Quicktools |  | Not needed - is primarily part of maintenance/post onboarding | xRemoved
69 |  | Quiz: O&M or not |  |  | xRemoved
77 |  | Quiz: Other EG teams |  |  | xRemoved
70 |  | Quiz: Prioritization |  |  | xRemoved
102 |  | Quiz: Refresh needed? |  |  | xRemoved
109 |  | Self-review exercise |  |  | xRemoved
88 |  | SQL exercise |  | Do it once the query is out | xRemoved
100 |  | Star ratings |  | Not needed - we are currently not doing star ratings for VRs | xRemoved
72 |  | Training cases: Business model conversions |  |  | xRemoved
107 |  | Training cases: Change History |  | Not needed-evaluate later | xRemoved
113 |  | Training cases: Data validation |  |  | xRemoved
116 |  | Training cases: Display logic |  |  | xRemoved
21 |  | Training cases: Excel basics |  | Pending asking vendor | xRemoved
22 |  | Training cases: Excel basics (continued) |  | Pending asking vendor | xRemoved
120 |  | Training cases: Failed BNs |  | Not required | xRemoved
103 |  | Training cases: Pushbacks |  |  | xRemoved
123 |  | Training debrief |  |  | xRemoved
110 |  | Validating partner data |  | Not needed - training mostly focuses on CL data dumps, VR requests are too different | xRemoved
124 |  | Xpresso rebuilt |  | simple and quick

## Day Skeleton (hidden)
Week1 | Focuse on basics
Week2 | Focuse on basics
Week3 | Focus VR specific
Week4 | Include shadowing
London |  | Singapore |  | Lima/Springfield |  | 2023-04-24
Start Time | End Time | Start Time | End Time | Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions
12:00 | 12:30 | 19:00 | 19:30 | 6:00 | 6:30 |  |  | recap day before / check training case from yesterday afternoon
12:30 | 14:00 | 19:30 | 21:00 | 6:30 | 8:00 |  |  | topic 1 - bigger topic
14:00 | 15:00 | 21:00 | 22:00 | 8:00 | 9:00 |  |  | topic 2
15:00 | 15:45 | 22:00 | 22:45 | 9:00 | 9:45 |  | Self | training cases on topic 1-2
15:45 | 16:00 | 22:45 | 23:00 | 9:45 | 10:00 |  |  | review training cases results
16:00 | 17:00 | 23:00 | 0:00 | 10:00 | 11:00 |  |  | Topic 3
17:00 | 18:00 | 0:00 | 1:00 | 11:00 | 12:00 |  |  | Topic 4
18:00 | 19:00 | 1:00 | 2:00 | 12:00 | 13:00 | Lunch | - | Lunch
19:00 | 20:00 | 2:00 | 3:00 | 13:00 | 14:00 |  | Self | Quiz/video
20:00 | 21:00 | 3:00 | 4:00 | 14:00 | 15:00 |  | Self | training cases on topic 3-4

## Blank Week (hidden)
Zoom Link | https://expedia.zoom.us/j/95059633936?pwd=K2F5WkxENEx2d3pnbzFnNG5VSlAzZz09
Meeting ID | 950 5963 3936
Passcode | 121212
London |  | Singapore |  | Lima/Springfield |  | 2023-04-24
Start Time | End Time | Start Time | End Time | Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions
12:00 | 12:30 | 19:00 | 19:30 | 6:00 | 6:30 | Questions from the last Friday? / Review Afternoon Training cases |  | recap day before / check training case from yesterday afternoon
12:30 | 14:00 | 19:30 | 21:00 | 6:30 | 8:00 |  |  | topic 1 - bigger topic
14:00 | 15:00 | 21:00 | 22:00 | 8:00 | 9:00 |  |  | topic 2
15:00 | 15:45 | 22:00 | 22:45 | 9:00 | 9:45 |  | Self | training cases on topic 1-2
15:45 | 16:00 | 22:45 | 23:00 | 9:45 | 10:00 |  |  | review training cases results
16:00 | 17:00 | 23:00 | 0:00 | 10:00 | 11:00 |  |  | Topic 3
17:00 | 18:00 | 0:00 | 1:00 | 11:00 | 12:00 |  |  | Topic 4
18:00 | 19:00 | 1:00 | 2:00 | 12:00 | 13:00 | Lunch | - | Lunch
19:00 | 20:00 | 2:00 | 3:00 | 13:00 | 14:00 |  | Self | Quiz/video
20:00 | 21:00 | 3:00 | 4:00 | 14:00 | 15:00 |  | Self | training cases on topic 3-4
London |  | Singapore |  | Lima/Springfield |  | 2023-04-25
Start Time | End Time | Start Time | End Time | Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions
12:00 | 12:30 | 19:00 | 19:30 | 6:00 | 6:30 | Questions from the day before? / Review Afternoon Training cases |  | recap day before / check training case from yesterday afternoon
12:30 | 14:00 | 19:30 | 21:00 | 6:30 | 8:00 |  |  | topic 1 - bigger topic
14:00 | 15:00 | 21:00 | 22:00 | 8:00 | 9:00 |  |  | topic 2
15:00 | 15:45 | 22:00 | 22:45 | 9:00 | 9:45 |  | Self | training cases on topic 1-2
15:45 | 16:00 | 22:45 | 23:00 | 9:45 | 10:00 |  |  | review training cases results
16:00 | 17:00 | 23:00 | 0:00 | 10:00 | 11:00 |  |  | Topic 3
17:00 | 18:00 | 0:00 | 1:00 | 11:00 | 12:00 |  |  | Topic 4
18:00 | 19:00 | 1:00 | 2:00 | 12:00 | 13:00 | Lunch | - | Lunch
19:00 | 20:00 | 2:00 | 3:00 | 13:00 | 14:00 |  | Self | Quiz/video
20:00 | 21:00 | 3:00 | 4:00 | 14:00 | 15:00 |  | Self | training cases on topic 3-4
London |  | Singapore |  | Lima/Springfield |  | 2023-04-26
Start Time | End Time | Start Time | End Time | Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions
12:00 | 12:30 | 19:00 | 19:30 | 6:00 | 6:30 | Questions from the day before? / Review Afternoon Training cases |  | recap day before / check training case from yesterday afternoon
12:30 | 14:00 | 19:30 | 21:00 | 6:30 | 8:00 |  |  | topic 1 - bigger topic
14:00 | 15:00 | 21:00 | 22:00 | 8:00 | 9:00 |  |  | topic 2
15:00 | 15:45 | 22:00 | 22:45 | 9:00 | 9:45 |  | Self | training cases on topic 1-2
15:45 | 16:00 | 22:45 | 23:00 | 9:45 | 10:00 |  |  | review training cases results
16:00 | 17:00 | 23:00 | 0:00 | 10:00 | 11:00 |  |  | Topic 3
17:00 | 18:00 | 0:00 | 1:00 | 11:00 | 12:00 |  |  | Topic 4
18:00 | 19:00 | 1:00 | 2:00 | 12:00 | 13:00 | Lunch | - | Lunch
19:00 | 20:00 | 2:00 | 3:00 | 13:00 | 14:00 |  | Self | Quiz/video
20:00 | 21:00 | 3:00 | 4:00 | 14:00 | 15:00 |  | Self | training cases on topic 3-4
London |  | Singapore |  | Lima/Springfield |  | 2023-04-27
Start Time | End Time | Start Time | End Time | Start Time | End Time | Session Name | Who | Goal(s) for this session | Notes/feedback/questions
12:00 | 12:30 | 19:00 | 19:30 | 6:00 | 6:30 | Questions from the day before? / Review Afternoon Training cases |  | recap day before / check training case from yesterday afternoon
12:30 | 14:00 | 19:30 | 21:00 | 6:30 | 8:00 |  |  | topic 1 - bigger topic
14:00 | 15:00 | 21:00 | 22:00 | 8:00 | 9:00 |  |  | topic 2
15:00 | 15:45 | 22:00 | 22:45 | 9:00 | 9:45 |  | Self | training cases on topic 1-2
15:45 | 16:00 | 22:45 | 23:00 | 9:45 | 10:00 |  |  | review training cases results
16:00 | 17:00 | 23:00 | 0:00 | 10:00 | 11:00 |  |  | Topic 3
17:00 | 18:00 | 0:00 | 1:00 | 11:00 | 12:00 |  |  | Topic 4
18:00 | 19:00 | 1:00 | 2:00 | 12:00 | 13:00 | Lunch | - | Lunch
19:00 | 20:00 | 2:00 | 3:00 | 13:00 | 14:00 |  | Self | Quiz/video
20:00 | 21:00 | 3:00 | 4:00 | 14:00 | 15:00 |  | Self | training cases on topic 3-4
London |  | Singapore |  | Lima/Springfield |  | 2023-04-28
Start Time | End Time | Start Time | End Time | Start Time | End Time | Session Name | Who |  | Notes/feedback/questions
12:00 | 12:30 | 19:00 | 19:30 | 6:00 | 6:30 | Check-in with Manager | YiQi
12:30 | 13:00 | 19:30 | 20:00 | 6:30 | 7:00 | Questions from the day before? / Review Afternoon Training cases |  | recap day before / check training case from yesterday afternoon
13:00 | 14:00 | 20:00 | 21:00 | 7:00 | 8:00 |  |  | topic 1
14:00 | 15:00 | 21:00 | 22:00 | 8:00 | 9:00 |  |  | topic 2
15:00 | 15:45 | 22:00 | 22:45 | 9:00 | 9:45 |  | Self | training cases on topic 1-2
15:45 | 16:00 | 22:45 | 23:00 | 9:45 | 10:00 |  |  | review training cases results
16:00 | 17:00 | 23:00 | 0:00 | 10:00 | 11:00 |  |  | Topic 3
17:00 | 18:00 | 0:00 | 1:00 | 11:00 | 12:00 |  |  | Topic 4
18:00 | 19:00 | 1:00 | 2:00 | 12:00 | 13:00 | Lunch | - | Lunch
19:00 | 20:00 | 2:00 | 3:00 | 13:00 | 14:00 |  | Self | Quiz/video
20:00 | 21:00 | 3:00 | 4:00 | 14:00 | 15:00 |  | Self | training cases on topic 3-4